| Meeting Date: | 20 July 2020 |
| --- | --- |
| Present: | D Rankin, K Gould, W Lumley, F Colliver, L Carlson, H Adams |
| Next meeting: | Every Weds, 1000AM MS/DT, ZOOM |

Proposed Standard Agenda – Ongoing Tasking Review

- Website facelift by 8/15

  - AGG will continue work with current peregrine.aero website to ensure continuity and availability of information

  - Update and maintain with current and evolving announcements

  - Post press releases and news information to the website

  - Incorporate Constant Contact “landing pages” to correlate the emailed message

  - Webinar announcements and webinar archive

  - While maintaining and improving the current website, the new website will be active by 10/10/20

    - Schedule & milestone review, facelift & new, as required

- At least monthly email campaigns (Constant Contact & LinkedIn) per agreed schedule

  - DRAFT plan review, suggested topics, targeted dates for release

- Up to ten Press Releases per agreed schedule and as frequently as bi-weekly by 12/31/2020

  - AGG will draft press release information featuring Peregrine announcements for approval by Peregrine prior to filing

  - Peregrine will provide essential press contacts for AGG to include in press release distribution

  - DRAFT plan review, suggested topics, target dates for PRs

- As frequently as monthly, AGG proposes three webinars per agreed schedule by 12/31/2020

  - DRAFT plan review, suggested topics, target dates for PRs

- Transmit to Peregrine all sales inquiries and prospects

  - DRAFT Process, Timing

- Where appropriate, arrange Zoom meetings with significant sales prospects

Special Topics To Be Addressed

  - Peregrine www site renovation and rebuild

    - Requirements capture, expectations discussion

    - Review strawman schedule for facelift & new build

  - Reason for the added topic(s) and any special info to share with group; new developments, etc.

Meeting Results

- Website Facelift

- Email Campaigns (Constant Contact & LinkedIn)

- Press Releases

- Webinars

- Sales Inquiries & Prospects

- Zoom Meetings - Sales Prospects

- Special Topics Discussion

Summarize the discussion for each issue, state the outcome, and note actions required

- Actions/ Responsible Individual/ ECD

List agreed or assigned action items, conditions, ECD