| Meeting Date: | 09DEC20 |
| --- | --- |
| Present: | D Rankin, K Gould, W Lumley, L Carlson, H Adams |
| Next meeting: | Proposed 17FEB21, 9AM MDT - ZOOM |

Proposed Standard Agenda – Ongoing Tasking Review - RELAUNCH

- Kevin and Forrest not available for 09 Dec review

- Website 2.0 – Review meeting held 08 Dec/ FC not available for 09 Dec review (WIP WWW)

  - WIP/ Brief FC lead, update as needed

      - Separate dedicated meeting weekly, for details

      - FC requested setting up an FTP location for all photos available at Peregrine.

        - Completed – review of content by LC/ FC at next review

- (Refresh) At least monthly email campaigns (Constant Contact & LinkedIn) per agreed schedule – LC update 09 Dec

  - DRAFT plan review, suggested topics, targeted dates for release

    - Draft Plan – New ECD

    - EMB, ODA, ACA, FDM, G150 Htr, TCAS 7.1, flt dk updates …

    - LC to update at next review

- (Refresh) Up to ten Press Releases per agreed schedule and as frequently as bi-weekly by 12/31/2020 – LC update 09 Dec

  - New Planning Schedule

  - Asked for any idea inputs ASAP (LC is collection POC)

  - Targeting reduced press releases through end CY 2020, excluding ODA major PR

  - AGG will draft press release information featuring Peregrine announcements for approval by Peregrine prior to filing

  - Peregrine will provide essential press contacts for AGG to include in press release distribution

    - Initial PR contact list/ Complete

- Transmit to Peregrine all sales inquiries and prospects – Complete/ Continuous Action

  - ZOHO confirmed as the vehicle for controlling the process – Reconfirm? (Confirmed)

    - Planned date for process in place/ TBD/ Update 09 Sept/ HA, LC - Update

- Where appropriate, arrange Zoom meetings with significant sales prospects

  - As required (Actions? Still an objective?)

Special Topics To Be Addressed (Needs Refresh)

Reason for the added topic(s) and any special info to share with group; new developments, etc.

- TCAS 7.1 – Mexico – LC Updates?

  - 01 Jan 2022 Mandate Deadline

  - Contacts email blast to key aircraft type owner/ operators

    - Learjet, Hawker, Citation, EMB

    - Communicating with Ric Peri

      - Appears mandate is less urgent, delayed

        - Applies to Mex reg aircraft only

        - Will send 7.1 update emails reminders

        - Update 09SEP Zoom/ LC

    - LC lead/ using JetNet data base (JNDB)

      - Complete – DB use is WIP/ LC

      - Update 09SEP Zoom/ LC

- ODA WIP Update – DR Update

  - Review of Peregrine FAA responses planned for next week

  - TEXTRON

    - Strong interest indicated in Peregrine ODA assist

      - Jake Biggs/ Manager, Aftermarket

      - Provide updates to Biggs/ HA as needed

  - Other Targets? Action Needed

- ACA (Aviation Clean Air)

  - RTCA SC241/ EUROCAE WG-121 Update – HA

    - Boeing informal feedback re ACA device (see need for ACA aerosol testing data below – HA

  - ACA Situation Update - WL

  - Track events to ID targets/ Update - ALL

  - Learjet med evac operation potential customer – WL update

    - Medevac use may provide “proof statement”/ support sales efforts

      - Operator is willing to provide aircraft, flight expenses(?) for testing ACA

        - ACA feedback re process & expense coverage WIP

          - Update 09 DEC Zoom/ Wes

    - Peregrine needs to provide aerosolized COVID-19 virus testing data

      - Contact ACA, secure feedback/ data

        - Completed/ Wes

        - Provide lab test data to medevac entity/ TBD?

        - Reference doc supplied for us in RTCA guidance efforts – HA update 09DEC

        - Foundation for white paper, possible Webinar(?)

  - TEXTRON – WL update

    - Telecon held 26 August/ Mike Gibbons/ Business Dvpt

      - Peregrine participants/ Wes, Kevin, Hal

      - Interest in most of product lines and XL (Jim Lee – beta fit), X, Sovereign seemed to be particular interest

      - Peregrine proposal requested/ due TBD/ Wes

        - Excluding the ACA device which TEXTRON procures direct from ACA