| Meeting Date: | 02 Sept 2020 |
| --- | --- |
| Present: | D Rankin, K Gould, W Lumley, L Carlson, H Adams |
| Next meeting: | 09SEP20, 9AM MDT - ZOOM |

Proposed Standard Agenda – Ongoing Tasking Review

- Website (current) facelift

  - AGG will continue work with current peregrine.aero website to ensure continuity and availability of information

    - WIP/ FC lead, update as needed

  - Update and maintain with current and evolving announcements

  - Post press releases and news information to the website

    - Press Releases Updated to www site/ FC ECD 03SEP20

  - Webinar announcements and webinar archive

    - TBD/ Webinar DRAFT Plan – ECD update/ 09SEP zoom/ LC, HA

      - Asked for any idea inputs ASAP (LC is collection POC)

      - WIP Updates as needed

    - Launch Webinar using EMB-120 flt dk update, in collaboration with Garmin

      - Initial planning WIP/ update 09SEP Zoom/ LC

  - While maintaining and improving the current website, the new website will be active by 10/10/20

    - Schedule & milestone review, facelift & new, as required

    - DRAFT Plan WIP – update/ Dependency – Brainstorming / FC, LC, HA

      - DRAFT agenda for brainstorming session/ As Needed/ FC

      - Brainstorming Session – All/ Target 10 or 11 Sept/ FC lead

- At least monthly email campaigns (Constant Contact & LinkedIn) per agreed schedule

  - DRAFT plan review, suggested topics, targeted dates for release

    - Draft plan WIP – draft plan to team/ 09SEP Zoom/ LC, HA

    - EMB, ODA, ACA, FDM, G150 Htr, TCAS 7.1, flt dk updates …

- Up to ten Press Releases per agreed schedule and as frequently as bi-weekly by 12/31/2020

  - Asked for any idea inputs ASAP (LC is collection POC)

  - Targeting reduced press releases through end CY 2020, excluding ODA major PR

  - AGG will draft press release information featuring Peregrine announcements for approval by Peregrine prior to filing

  - Peregrine will provide essential press contacts for AGG to include in press release distribution

    - Initial PR contact list/ Complete

  - DRAFT plan review, suggested topics, target dates for PRs

    - Harmonize with email campaigns re timing, content, etc.

    - DRAFT Plan WIP/ LC lead – update/ 09SEP Zoom/ LC, HA

- Transmit to Peregrine all sales inquiries and prospects

  - DRAFT Process, Timing

  - ZOHO confirmed as the vehicle for controlling the process

    - Planned date for process in place/ TBD/ Update 09 Sept/ HA, LC

- Where appropriate, arrange Zoom meetings with significant sales prospects

  - As required

Special Topics To Be Addressed

Reason for the added topic(s) and any special info to share with group; new developments, etc.

- Peregrine www site renovation and rebuild

  - Requirements capture, expectations discussion

  - Review strawman schedule for facelift & new build

  - WIP/ Update 09SEP Zoom/ FC, Lead

- TCAS 7.1 – Mexico

  - 01 Jan 2022 Mandate Deadline

  - Contacts email blast to key aircraft type owner/ operators

    - Learjet, Hawker, Citation, EMB

    - Communicating with Ric Peri

      - Appears mandate is less urgent, delayed

        - Applies to Mex reg aircraft only

        - Will send 7.1 update emails reminders

        - Update 09SEP Zoom/ LC

    - LC lead/ using JetNet data base (JNDB)

      - Complete – DB use is WIP/ LC

      - Update 09SEP Zoom/ LC

- ODA WIP Update

  - Review of Peregrine FAA responses planned for next week

  - Targeting submission in week or two

  - New DEN ACO Manager – Sue McCormick

    - Known entity, previous work with Dave R - cooperative

    - Should now see some progress on ODA, at FAA end

  - TEXTRON

    - Strong interest indicated in Peregrine ODA assist

      - Jake Biggs/ Manager, Aftermarket

      - Provide updates to Biggs/ HA as needed

- ACA (Aviation Clean Air)

  - Ionization device, in-line with ECS

    - Peregrine providing engineering services (STC, kits) and possibly the end ACA device

  - DRAFT Briefing Complete/ HA lead – inputs as needed

  - Two key issues a challenge for ACA solution promotion

    - Large fleets require very long retrofit schedules

      - Long term pandemic impacts, worldwide, even with vaccine, will likely provide more “runway” for the ACA solution/ TBC

      - Emphasis on recurring pathogen pandemics – futureproof

    - Aerosolized virus testing/ Provided/ Wes

      - First lab effectivity testing of virus aerosols completed

        - Reviewed, issues noted/ HA 01SEP20

  - Regional airlines targets – Dropped by Major Airline Downsizing

    - Dropped regionals will likely compete on own operation

      - ACA solution has good potential to differentiate

    - Track events to ID targets/ Update 09SEP Zoom/ ALL

  - Learjet med evac operation potential customer

    - Medevac use may provide “proof statement”/ support sales efforts

      - Operator is willing to provide aircraft, flight expenses(?) for testing ACA

        - ACA feedback re process & expense coverage WIP

          - Update 09 SEP Zoom/ Wes

    - Peregrine needs to provide aerosolized COVID-19 virus testing data

      - Contact ACA, secure feedback/ data

        - Completed/ Wes

        - Provide lab test data to medevac entity/ TBD?

      - Secondary mkt research – ACA site, GPS site, scientific data

        - WIP/ HA lead – Update 09 SEP Zoom, Info Distr As Available/ HA

        - Foundation for white paper, possible Webinar(?)

  - TEXTRON

    - Telecon held 26 August/ Mike Gibbons/ Business Dvpt

      - Peregrine participants/ Wes, Kevin, Hal

      - Interest in most of product lines and XL (Jim Lee – beta fit), X, Sovereign seemed to be particular interest

      - Peregrine proposal requested/ due TBD/ Wes

        - Excluding the ACA device which TEXTRON procures direct from ACA