| Meeting Date: | 12 AUG 2020 |
| --- | --- |
| Present: | D Rankin, K Gould, W Lumley, L Carlson, H Adams |
| Next meeting: | 19AUG20, 9AM MDT - ZOOM |

Proposed Standard Agenda – Ongoing Tasking Review

- Website facelift by 8/15

  - AGG will continue work with current peregrine.aero website to ensure continuity and availability of information

    - WIP/ FC lead, update as needed

  - Update and maintain with current and evolving announcements

    - EMB-120 short video link fix WIP/ FC ECD 07 Aug, Friday

  - Post press releases and news information to the website

    - WIP/ EMB-120 PR/ LC draft to be sent as soon as approved

      - Constant Contact + PR Contact List

    - Awaiting Worldwide approval of PR

  - Incorporate Constant Contact “landing pages” to correlate the emailed message

    - Complete

  - Webinar announcements and webinar archive

    - TBD/ Webinar DRAFT Plan – ECD update/ 12 Aug zoom/ LC, HA

      - Asked for any idea inputs ASAP (LC is collection POC)

  - While maintaining and improving the current website, the new website will be active by 10/10/20

    - Schedule & milestone review, facelift & new, as required

    - DRAFT Plan WIP – update/ 26 Aug Zoom/ LC, HA

      - DRAFT agenda for brainstorming session/ 24 Aug/ FC

      - Brainstorming Session – All/ 27 Aug/ FC lead

- At least monthly email campaigns (Constant Contact & LinkedIn) per agreed schedule

  - DRAFT plan review, suggested topics, targeted dates for release

    - Draft plan WIP – update/ 12 Aug Zoom/ LC, HA

- Up to ten Press Releases per agreed schedule and as frequently as bi-weekly by 12/31/2020

  - Asked for any idea inputs ASAP (LC is collection POC)

  - AGG will draft press release information featuring Peregrine announcements for approval by Peregrine prior to filing

  - Peregrine will provide essential press contacts for AGG to include in press release distribution

    - Initial PR contact list/ Complete

  - DRAFT plan review, suggested topics, target dates for PRs

    - DRAFT Plan WIP/ LC lead – update/ 12 Aug Zoom/ LC, HA

- Transmit to Peregrine all sales inquiries and prospects

  - DRAFT Process, Timing

  - ZOHO confirmed as the vehicle for controlling the process

  - Planned date for process in place/ TBD/ Update 12 Aug/ HA, LC

- Where appropriate, arrange Zoom meetings with significant sales prospects

  - As required

Special Topics To Be Addressed

  - Peregrine www site renovation and rebuild

    - Requirements capture, expectations discussion

    - Review strawman schedule for facelift & new build

  - Reason for the added topic(s) and any special info to share with group; new developments, etc.

- Special Topics

  - TCAS 7.1 – Mexico

    - 01 Jan 2022 Mandate Deadline

    - Contacts email blast to key aircraft type owner/ operators

      - Learjet, Hawker, Citation, EMB

      - LC lead/ using JetNet data base (JNDB)

        - Complete – DB use is WIP/ LC

        - Update 12 Aug Zoom/ LC

  - ACA

    - DRAFT Briefing Complete/ HA lead – inputs as needed

    - Two key issues a challenge for ACA solution promotion

      - Large fleets require very long retrofit schedules

        - Long term pandemic impacts, worldwide, even with vaccine, will likely provide more “runway” for the ACA solution/ TBC

      - Aerosolized virus testing/ update 12 Aug/ WL

        - A Learjet medevac operator is willing to provide aircraft, flight expenses(?) for testing ACA

          - ACA feedback re process & expense coverage WIP

            - Update 12 Aug Zoom/ WL

    - Regional airlines targets – Dropped by Major Airline Downsizing

      - Dropped regionals will likely compete on own operation

        - ACA solution has good potential to differentiate

      - Track events to ID targets/ Update 12 Aug/ ALL

    - Learjet med evac operation potential customer

      - Medevac use may provide “proof statement”/ support sales efforts

      - Peregrine needs to provide aerosolized COVID-19 virus testing data

      - Contact ACA, secure feedback/ data

        - WIP/ update 12 Aug Zoom/ WL

      - Secondary mkt research – ACA site, GPS site, scientific data

        - WIP/ HA lead – Update 12 Aug Zoom, Info Distr As Available/ HA

        - Foundation for white paper, possible Webinar(?)

    - TEXTRON/ Jake Biggs

      - WIP re discovery of areas where Peregrine may assist in aftermarket mods

      - Jake Biggs Zoom scheduled for 10 March

        - Update 12 Aug Zoom & meeting report/ HA, LC