## Sheet1
ID | Chapter | Action | Who | Status | When (COB) | Comments
1 | 8 | Discussion of buying processes for different groups, what they value and how they make decisions (airlines, freighter conversion, biz jet, etc) | L | TBD | 2024-09-11
2 | 11 | Retrofit/upgrade section and an aftermarket section that seem to be saying very similar things; reconcile this into a more coherent structure | L | TBD | 2024-09-10
3 | 11 | Take‐up of HUDs among airlines | F | TBD | 2024-09-10
4 | 11 | Single pilot operations (freight) | F | TBD | 2024-09-10
5 | 11 | COVID adjustment to the aftermarket (revise current COVID Section) | L | TBD | 2024-09-10
6 | 11 | International ATC Evolution | F | TBD | 2024-09-11
7 | Exec Summary | Develop key points/trends from the analysis (Aerospace Edge Input) | L/F | TBD | 2024-09-10
8 | Integration | Integrate chapter material into Overleaf document | L/F | TBD | 2024-09-12
9 | Model | Review main model output from Joanne and suggest any changes as needed. | L/F | Clarify |  | Aerospace Edge analysis complete; discuss during 10 Sep team call.
10 | Model | Review market share analysis | L/F | Clarify |  | Assess this during 10 Sep team call.
11 | Profiles | Profile Review by SMEs (NA/EU/ROW) | L/F | Clarify |  | Assess this during 10 Sep team call.